# - General Requirements

## General

### Basic Services to be provided by the Commissioning Agent (“CxA”) shall consist of the activities and stages set forth in Article 2, including normal fundamental and enhanced commissioning services for the Project.

## Consultation

### The CxA shall attend regular meetings with the A/E, Contracting Authority, and Owner. The CxA shall consult with the Contracting Authority, Owner, and A/E regarding Site use and improvements and the selection of materials, building systems, and equipment. The CxA shall provide recommendations to the Contracting Authority, Owner, and A/E on construction feasibility; actions designed to minimize adverse effects of labor or material shortages; time requirements for procurement, installation and construction completion; and factors related to construction cost, including estimates of alternative designs or materials, budgets and possible economies.

### At all appropriate times throughout performance of the Services, the CxA shall contact, meet, consult, and otherwise coordinate with the Contracting Authority, Owner, A/E, CM if any, governmental authorities with jurisdiction over the Project, and others for the purpose of facilitating the Project’s design and construction.

### The CxA shall provide reports and other Project information through the Contracting Authority’s web-based tools including the following:

#### The State’s web-based project management system.

# - Basic Services

## Overview

### Commissioning is a quality assurance process that works to ensure that the building’s design intent is fully realized. A systematic approach is employed to review, verify and document that the specified components and systems have been designed, installed, started up properly and then functionally tested to verify and document proper operation through all modes and conditions. A final commissioning report document or Systems Manual is produced that will outline the events and findings of the commissioning project. It will include an accounting of all findings, final resolutions and recommendations. Commissioning does not replace or eliminate any requirements for reviews, inspections or other quality control measures by any other firm, organization, or party. The A/E, CM if any, Contractors, and Project Manager, as applicable, maintain their obligations as a function of their roles and responsibilities. The process begins in the design stages and extends through project completion, closeout, and warrantee reviews. Functional testing of the systems includes actual seasonal systems tests.

## Sustainable Design Requirements

### This Project shall be designed and constructed in accordance with the requirements of Am. Sub. H.B. 251 of the 126th General Assembly and the resulting rules, policies, and procedures adopted by the Ohio Facilities Construction Commission establishing Sustainability Requirements for Capital Improvements Projects, including applicable provisions of OAC Section 3318-3.

### The U.S. Green Building Council (“USGBC”) has adopted commissioning requirements and enhanced commissioning credits for all buildings that are certified under its Leadership in Energy and Environmental Design (“LEED®”) rating system. Buildings may become certified through LEED at the “Certified,” “Silver,” “Gold,” and “Platinum” levels. People working in the green building field may become LEED-Accredited Professionals (“LEED AP”) with or without a specialty.

### The sustainability goals established for this Project by the Owner are (1) to obtain LEED Silver Certification with an emphasis in Energy and Atmosphere (EA) credits, and (2) to comply with LEED New Construction Energy and Atmosphere credit 3 (EAcr3) for Enhanced Commissioning in addition to the fundamental commissioning prerequisite for LEED certification. The CxA is responsible for the following:

#### EA Prerequisite 1 – Fundamental Commissioning –Verify that the building’s energy-related systems are installed, calibrated and perform according to the Owner’s Project Requirements (“OPR”), Basis of Design (“BOD”), and construction documents. In order to meet this requirement, the CxA will: (1) review the OPR and BOD for clarity and completeness and provide comments to the Owner, (2) develop and incorporate commissioning requirements into the construction documents, (3) develop and implement a commissioning plan, (4) verify installation and performance of the systems to be commissioned, and (5) complete a summary commissioning report.

#### EA Credit 3 (EAcr3) – Enhanced Commissioning – Begin the commissioning process early during the design process and execute additional activities after systems performance verification is completed. In order to achieve this credit, the CxA will: (1) conduct, at a minimum, one commissioning design review of the OPR, BOD, and design documents at 50 percent completion of the Construction Documents Stage and back-check the review comments in the subsequent design submission, (2) review Contractor submittals applicable to systems being commissioned for compliance with the OPR and BOD, (3) develop a systems manual that provides future operating staff the information needed to understand and optimally operate commissioned systems, (4) verify requirements for training operating personnel and building occupants are completed, and (5) review building operation within 10 months after Substantial Completion with operating staff and occupants, including a plan for resolution of outstanding commissioning-related issues.

### The CxA serves as the Owner’s contractual representative and as such will act in the Owner’s best interest by following accepted industry and professional standards and meeting the LEED Enhanced Commissioning requirements as defined in the appropriate version of LEED. The CxA will work with the design team to upload appropriate information into the LEED online web tool as required for the submittal for LEED certification.

### The CxA shall provide professional commissioning services in order to confirm that major building systems in newly completed facilities are good operational systems that are low on maintenance and operating costs and perform interactively according to the Contract Documents.

### The CxA is not an employee of or in contract with the A/E, or CM if any, on the project and will work independently from both; however, the CxA will collaborate with both throughout the design and construction process to meet deadlines and provide feedback to the Owner and the design team as the process moves forward.

### The CxA shall perform services with professional standards of skill, care and reasonable diligence in accordance with generally accepted commissioning practices, the terms of this Agreement.

### Basic Commissioning Services provided by the CxA are defined as services starting in the design stage through seasonal testing. The CxA shall review design documents, develop a commissioning specification, and develop and coordinate the execution of a testing plan, which includes observing and documenting system’s performance to ensure that systems are functioning in accordance with the design intent of the Contract Documents and the Owner’s objectives.

### The CxA may provide commissioning services through one or more Consultants employed by the CxA. Any Consultant shall be an independent party with no affiliations to a design team or participating contractors in a facilities program. All Consultants shall be approved by the Contracting Authority before providing services. The Contracting Authority retains the discretion to reject the services of a Consultant to provide commissioning services. The Contracting Authority, in consultation with the Owner, retains the discretion to reject a Consultant for a specific project.

### The CxA is not responsible for design or general construction scheduling, cost estimating, construction management, or performing corrective work, but may assist with problem solving or addressing non-conformance issues or deficiencies.

### The CxA shall provide Basic Commissioning Services under this Agreement for the following systems:

#### Heating, ventilating, air conditioning, and refrigeration (“HVAC&R”) systems, mechanical and passive, and associated controls;

#### Lighting and daylighting controls;

#### Domestic hot water systems;

#### Renewable energy systems if applicable; and

#### Emergency power systems.

### The CxA shall perform commissioning tasks in general conformance with the following schedule:

#### Design Stages:

##### Assist the Owner with development of the OPR and BOD,

##### Develop Project-specific commissioning specifications, and

##### Develop the Commissioning Plan.

#### Construction Stage:

##### Develop Pre-Functional and Functional Testing procedures,

##### Coordinate commissioning activities,

##### Verify installation requirements were achieved,

##### Verify operation of all commissioned systems,

##### Validate testing and balancing through independent system testing, and

##### Communicate and track deficiencies.

#### Occupancy and Operation Stage:

##### Seasonal testing,

##### Monitoring of space conditions through data-loggers, and

##### Verification that all deficiencies have been closed out.

## Design Review

### The CxA shall:

#### Provide review and analysis of the A/E’s design documents including, but not limited to, drawings, specifications, and other design submittals at the conclusion of each of the following stages:

##### Program Verification Stage,

##### Schematic Design Stage,

##### Design Development Stage, and

##### Construction Documents Stage

#### Attend meetings with the Contracting Authority, Owner, A/E, and CM if any; and

#### Provide reports and checklists related to its activities at this stage to the Owner.

### If the Project is administered using the State’s web-based project management system, the CxA shall receive and review the A/E’s design documents and submit its comments to the A/E, CM if any, Owner, and Contracting Authority through the “Design Reviews” business process.

## Pre-Functional Testing

### During Pre-Functional Testing, the CxA shall:

#### Review and analyze submittal documents;

#### Attend meetings with the Contracting Authority, Owner, A/E, and CM if any;

#### Perform site visits and equipment, systems and work verifications; and

#### Provide reports and checklists related to its activities at this stage to the Owner.

## Functional Testing

### During Functional Testing, the CxA shall:

#### Review and analyze submittal documents independent of the A/E, and CM if any;

#### Attend meetings with the Contracting Authority, Owner, A/E, and CM if any;

#### Perform site visits and conduct equipment, systems and work verifications;

#### Participate in systems and equipment start-up activities;

#### Perform functional testing, re-testing, and verifications; and

#### Provide reports and checklists related to its activities at this stage to the Owner.

### The CxA shall functionally test all major HVAC equipment and approximately 20 percent of miscellaneous equipment, including but not limited to variable air volume devices, exhaust fans, and similar equipment, to ensure proper installation and operation. If functional testing reveals consistent problems, the CxA shall test a larger sampling in accordance with established industry standards.

## Preliminary Report

### The CxA shall provide its Commissioning Report, except seasonal and warranty commissioning, to the Contracting Authority, Owner, A/E, CM if any, and affected Contractors.

## Seasonal Testing

### During Seasonal Testing, the CxA shall:

#### Attend meetings with the Contracting Authority, Owner, A/E, and CM if any;

#### Perform site visits and conduct equipment, systems and work verifications over the heating and cooling seasons during the first year of occupancy;

#### Perform functional testing, re-testing, and verifications; and

#### Provide reports and checklists related to its activities at this stage to the Owner.

## Final Report

### The CxA shall provide its final Commissioning Report, including seasonal and warranty commissioning, to the Contracting Authority, Owner, A/E, CM if any, and affected Contractors.

### Performance Evaluations.

#### The Contracting Authority shall evaluate the CxA’s performance during the progress of the Work, at completion of a phase of the Project, completion of the Project, or both. The Contracting Authority shall retain the evaluation(s).

##### The CxA may request a copy of the completed evaluation(s). If the CxA wishes to comment or take exception to any rating or remark, the CxA shall send a response in writing to the Contracting Authority within 30 days of receiving the evaluation(s).

##### The Contracting Authority may use the evaluation(s) in determining the qualifications of the CxA for future contracts.

##### The Contracting Authority may request information from the CxA for use in evaluating the Contractor’s or the Contracting Authority’s performance. If such information is requested, the CxA shall comply in a timely and responsive manner.

# - Additional Services

## General Requirements

### Services Not Included in Basic Services.

#### The CxA shall provide Commissioning of systems not listed in Article 2 as Additional Services only when identified in the Agreement Form or otherwise approved in writing by the Contracting Authority in consultation with the Owner.

#### The services listed in the Agreement Form shall be paid as provided in this Agreement, in addition to payment for the Basic Services; however, the CxA shall not be compensated for any Additional Services made necessary by any act or omission of the CxA or any of the CxA’s Consultants.

#### Unless waived by the Contracting Authority in writing, authorization to provide Additional Services must be obtained prior to providing the Additional Services.

END OF DOCUMENT